### Work Programme

The following Key Targets have been established for WS1:

KT 1.1: Archiving - maintain or improve upon 2012 levels of archiving across the DAC network, demonstrate use of centralised archiving guidelines. (Links to HL01, HLO2)

KT 1.2: Data Access - DACs demonstrate direct access to data and INSPIRE compliant view and download and agree timetable for further publishing. (Links to HL03)

KT 1.3: Accreditation - Provide support to at least one further DAC to join the network (e.g.  Northern Irish component of Heritage DAC, JNCC as a Bird DAC). (Links to HL04)

KT 1.4: Metadata quality – Update metadata records created by DACs to latest version of MEDIN Discovery Metadata Standard - achieve validation of metadata records in the new MEDIN portal. (Links to HL04 and HL07)

A)	Operational DAC networks

The DAC Network is operational.  The Work Programme covers support of the DAC network through reporting and central services.

OPERATIONAL TASKS

Archiving

- DAC archiving of MEDIN partner and third party data.  DACs continue to archive data to agreed individual programmes.  DACs are asked to detail archiving through the annual reports and engagement with MEDIN partners.  Archiving to be at or greater than the baseline 2012 archiving level.

- Provide central enquiry point, and generic online and downloadable guidance for DAC network and data submission (DR 17).

- Share best practice through the DAC network via DAC Working Group meetings.

Data Dissemination

- Disseminate data through MEDIN portal (working with Portal work stream) and DAC local portals, facilitating direct access to data from MEDIN portal.

- MEDIN helpdesk for data access enquiries (same as above, DR17)

Reporting and DAC Network Management

- Provide DAC Annual reports by May 2018

- Plan of (re)accreditation of existing and new DACs for 2018 (DR 18.)

- At least two DAC working group meetings.

- Continue to promote data archive funding model at MSCC level, including the need to allocate costs of archiving before data collection is initiated.

DEVELOPMENT TASKS

Archiving

- Increase submission of data and archiving from new suppliers/third parties, with a continuing focus on data collected by marine industries (Expanding MEDIN Coverage).

Data Dissemination

- DACs establish and release INSPIRE compliant view and download services, directly linked to portal metadata records (KR1, DR1, DR6) (Enhancing User Experience and Meeting Policy Requirements).

- Encourage wider re-use of data held within MEDIN DACs by holding events where the community is encouraged to access the data and build products. e.g. Support another MEDIN Codefest with WS6 Communications, with an emphasis on UKDMOS.

- Liaise and publish data for integration with existing/and emerging tools and initiatives (e.g. CefMAT and EMODNET) (Link with WS4).

- Publish centralised guidance on use of persistent identifiers for marine data to promote consistency across the DACs.

Reporting and DAC Network Management

- Review DAC accreditation process – e.g. consider adopting a wider accreditation process.

- DAC development. Working with existing DACs on developing roles/services.

- Consolidation of DAC Network Coverage

OPERATIONAL TASKS

- Complete the FishDAC to incorporate Northern Ireland and inshore data.

- Complete the Historic Environment DAC with Department for Communities, Northern Ireland and maintain links with Historic England.

DEVELOPMENT TASKS:

- Meet MSFD requirements by managing relevant data in DAC network where required and ensuring subsets of data used for assessments can be captured (Meeting Policy Requirements).

- Expand DAC data coverage by identifying data archiving solution for at least one of the data themes not currently covered by MEDIN DACs (socio-economic data, birds).

- Archive major new datasets.  DACs to confirm approach/coverage/funding, e.g. Marine Conservation Zone site survey data (Expanding MEDIN Coverage).

- Consider small data archiving projects with a focus on direct access to data (Expanding MEDIN Coverage).*

- Coordination with other Work Streams

OPERATIONAL TASKS

- Standards: Ensure DACs meet INSPIRE and international compliance, and deliver clear UK data standards for the collection, collation and archive of marine environmental data.

- Portal: Work with MEDIN portal to ensure MEDIN metadata standard is being consistently applied by the DACs. DACs to work to ensure 100% of metadata in portal passes new validation tool checks.

- Communications: Complete improvements to the DAC component of the MEDIN website.

DACs Deliverables Table 2018-19

| - Q1 Deliverables |  | - Status |  | - Commentary |
| --- | --- | --- | --- | --- |
| - DAC Annual Reports (2017-18) according to pro-forma (KT1.4) |  |  |  |  |
| - DAC working group meeting, to include session on persistent identifiers |  |  |  | - Planned for 26 April 2018 |
| Plan MEDIN codefest feasibility and implementation in Q3 to demonstrate how MEDIN data and metadata can be used by UK marine community and beyond, with a focus on UKDMOS (monitoring data) |  |  |  |  |
| Launch small data archiving project proposals from DACs with a focus on direct access to data including monitoring data* |  |  |  |  |
| Monitor progress with MEDIN metadata validation by holding teleconference with DACs |  |  |  |  |
| Liaise with WS6 to provide input to the MEDIN 10 year anniversary Partner’s meeting |  |  |  |  |
| - Q2 |  |  |  |  |
| - Reaccreditation outline plan for 2018 (KT1.3). Complete ADS reaccreditation |  |  |  |  |
| - Review progress with Northern Ireland FishDAC accreditation (KT1.3) |  |  |  |  |
| - Deliver MCZ / MPA data archiving progress report (KT1.1) |  |  |  |  |
| - Hold a Historic Environment DAC meeting and continue to review progress with expanding the Historic Environment DAC network coverage |  |  |  |  |
| - Implementation of changes to DAC webpages |  |  |  |  |
| Q3 |  |  |  |  |
| - DAC Working Group Meeting |  |  |  |  |
| - Hold 3rd MEDIN “Codefest” / DAC technical workshop and report findings based on options |  |  |  |  |
| - Identify MSFD datasets to be managed in the DAC network |  |  |  |  |
| - Review progress with validation of portal metadata records. |  |  |  |  |
| - Q4 |  |  |  |  |
| - WS1 report for 2018-19 |  |  |  |  |
| - DAC work plan for 2019-24 |  |  |  |  |

CefMAT – Cefas Marine Assessment Toolhttp://emeco.azurewebsites.net/

EMODNET - European Marine Observation and Data Network

* Tasks at risk from uncertain funding