# Work Stream Progress

## WS1 Network of Data Archive Centres

Deliverables Table 2018-19

| - Q1 Deliverables | - Status | - Commentary |
| --- | --- | --- |
| - DAC Annual Reports (2017-18) according to pro-forma (KT1.4) | - Achieved | - All DAC reports have been received. Main DAC report sent to Exec Team at end of September. |
| - DAC working group meeting, to include session on persistent identifiers | - Achieved | - Held on 25th April 2018 |
| Plan MEDIN codefest feasibility and implementation in Q3 to demonstrate how MEDIN data and metadata can be used by UK marine community and beyond, with a focus on UKDMOS (monitoring data) | - Achieved | - Codefest originally planned for Q3, but now more likely Q4 – aiming to use UKDMOS data. Attendance limited to MEDIN DACs due to budget constraints. |
| Launch small data archiving project proposals from DACs with a focus on direct access to data including monitoring data* | - Achieved | - Call for small data archiving projects was issued in mid-June 2018. 2 bids were received and 1 funded. |
| Monitor progress with MEDIN metadata validation by holding teleconference with DACs | - Achieved | - This was held as a discussion item on the DAC WG agenda. |
| Liaise with WS6 to provide input to the MEDIN 10 year anniversary Partner’s meeting | - Achieved | - DACs contributed to MEDIN Open meeting, held April 2018. |
| Q2 |  |  |
| Reaccreditation outline plan for 2018 (KT1.3). Complete ADS reaccreditation | - Achieved |  |
| Review progress with Northern Ireland FishDAC accreditation (KT1.3) | - Off track | - Postponed to Q3. Awaiting response from AFBI. |
| Deliver MCZ / MPA data archiving progress report (KT1.1) | - Achieved | - DASSH and BGS provided an update of progress with archiving MCZ data at a workshop with Cefas and JNCC in July 2018. |
| Hold a Historic Environment DAC meeting and continue to review progress with expanding the Historic Environment DAC network coverage | - On track | - Meeting planned for 20th November 2018 |
| Implementation of changes to DAC webpages | - Achieved | - New DAC web pages available: http://medin.org.uk/about/data-archive-centres |
| Q3 |  |  |
| DAC Working Group Meeting | - On track | - Meeting planned for 20th November 2018 |
| Hold 3rd MEDIN “Codefest” / DAC technical workshop and report findings based on options |  |  |
| Identify MSFD datasets to be managed in the DAC network |  |  |
| Review progress with validation of portal metadata records. |  |  |
| Review progress with Northern Ireland FishDAC accreditation (KT1.3) |  |  |
| Q4 |  |  |
| WS1 report for 2018-19 |  |  |
| DAC work plan for 2019-24 |  |  |