### Work Programme 2019-20

The following Key Targets have been established for WS1:

KT 1.1: Archiving -  Growing archive of data in MEDIN DACs with an emphasis on high quality data and metadata, demonstrate use of centralised archiving guidelines.

KT 1.2:  Data Access - DACs demonstrate direct access to data and INSPIRE compliant view and download.

KT 1.3: Accreditation - Provide support to at least one further DAC to join the network (e.g.  Northern Irish component of Heritage DAC, JNCC as a Bird DAC).

OPERATIONAL TASKS

Archiving

- DAC archiving of MEDIN partner and third party data.  DACs continue to archive data to agreed individual programmes.  DACs are asked to detail archiving through the annual reports and engagement with MEDIN partners.  Archiving to be at or greater than the baseline 2012 archiving level.

- Increase the proportion of directly available datasets (2 clicks to data)

- Provide central enquiry point, and generic online and downloadable guidance for DAC network and data submission.

- Share best practice through the DAC network via DAC Working Group meetings.

Data Dissemination

- Disseminate data through MEDIN portal (working with Portal work stream) and DAC local portals, facilitating direct access to data from MEDIN portal.

- Maintain MEDIN helpdesk for data access enquiries

Reporting and DAC Network Management

- Provide DAC Annual reports by May 2019

- Plan of (re)accreditation of existing and new DACs for 2019

- Hold at least two DAC working group meetings.

- Develop DAC Work Plan for 2020-21.

- Continue to promote data archive funding model at MSCC level, including the need to allocate costs of archiving before data collection is initiated.

- Deliver progress report on MCZ/MPA data archiving.

Consolidation of DAC network coverage

- FishDAC: Engage with Northern Ireland to complete the FishDAC accreditation application.

- Historic Environment DAC: Maintain links with Department for Communities, Northern Ireland and Historic England.

Coordination with other work streams

- Standards: Ensure DACs meet INSPIRE and international compliance and deliver clear UK data standards for the collection, collation and archive of marine environmental data.

- Portal: Work with MEDIN portal to ensure MEDIN metadata standard is being consistently applied by the DACs. DACs to work to ensure 100% of metadata in portal passes new validation tool checks.

- Communications: Complete improvements to the DAC component of the MEDIN website.

DEVELOPMENT TASKS

Archiving

- Proactively identify, target and engage with new suppliers to get their data onto the MEDIN portal.

- Increase submission of data and archiving from new suppliers/third parties, with a continuing focus on data collected by marine industries (Expanding MEDIN Coverage).

- Meet MSFD requirements by managing relevant data in DAC network where required and ensuring subsets of data used for assessments can be captured (Meeting Policy Requirements).

- Expand DAC data coverage by identifying data archiving solution for at least one of the data themes not currently covered by MEDIN DACs (socio-economic data, birds).

- Archive major new datasets.  DACs to confirm approach/coverage/funding, e.g. Marine Conservation Zone site survey data (Expanding MEDIN Coverage).

- Consider small data archiving projects with a focus on direct access to data (Expanding MEDIN Coverage).

Data Dissemination

- DACs establish and release INSPIRE compliant view and download services, directly linked to portal metadata records

- Encourage wider re-use of data held within MEDIN DACs by holding events where the community is encouraged to access the data and build products. e.g. Support another MEDIN Codefest with WS6 Communications, with an emphasis on UKDMOS data.*

- Liaise and publish data for integration with existing/and emerging tools and initiatives (e.g. CefMAT and EMODNET) (Link with WS4).

- Develop a DAC-wide approach to provenance tracking - Publish centralised guidance on use of persistent identifiers for marine data to promote consistency across the DACs.

Reporting and DAC Network Management

- Develop a data ingestion model, covering costs, timescales and capabilities for all DACs. *

- Review DAC accreditation process – e.g. consider adopting a wider accreditation process.

- Review implications of cloud adoption in the DAC network, ie revise MEDIN accreditation to include something on cloud technology for those DACs that use cloud technology. *

- DAC development. Working with existing DACs on developing roles/services.

- Horizon scanning for new technology approaches (e.g. schema.org), so that MEDIN is prepared to adapt to advances in technology.

Specific activities to deliver these Key Targets are summarised in the table below, along with a timeline for their duration. Note some activities are ongoing throughout the year.

DACs Activities and Timeline 2019-20

Activities in purple text are new to the DAC work plan, with the publication of the new MEDIN Business Plan 2019-2024.

Activities in italics are at risk if the MEDIN budget does not receive increased funding.

| Activity | Apr-19 | May-19 | Jun-19 | Jul-19 | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Maintain and expand a comprehensive DAC network |  |  |  |  |  |  |  |  |  |  |  |  |
| Increase the proportion of directly available datasets (2 clicks to data). |  |  |  |  |  |  |  |  |  |  |  |  |
| Validation of portal metadata records |  |  |  |  |  |  |  |  |  |  |  |  |
| DAC annual report collation and writing |  |  |  |  |  |  |  |  |  |  |  |  |
| Review progress with NI FishDAC accreditation |  |  |  |  |  |  |  |  |  |  |  |  |
| DAC WG meeting |  |  |  |  |  |  |  |  |  |  |  |  |
| Launch small data archiving projects* |  |  |  |  |  |  |  |  |  |  |  |  |
| Deliver progress report on MCZ/MPA data archiving |  |  |  |  |  |  |  |  |  |  |  |  |
| MSFD datasets to be managed in DAC network |  |  |  |  |  |  |  |  |  |  |  |  |
| NEW: Review implications of cloud adoption in the DAC network i.e. revise MEDIN accreditation should a DAC use cloud technology.* |  |  |  |  |  |  |  |  |  |  |  |  |
| NEW: Develop a DAC-wide approach to provenance tracking. |  |  |  |  |  |  |  |  |  |  |  |  |
| NEW: Proactively identify, target and engage with new suppliers to get their data on the MEDIN portal |  |  |  |  |  |  |  |  |  |  |  |  |
| NEW: Develop a data ingestion model, covering costs, timescales and capabilities for all DACs.* |  |  |  |  |  |  |  |  |  |  |  |  |
| NEW: Horizon scanning for new technology approaches e.g. schema.org, so that MEDIN is prepared to adapt to advances in technology[1]. |  |  |  |  |  |  |  |  |  |  |  |  |
| DAC work plan 2020-21 |  |  |  |  |  |  |  |  |  |  |  |  |

CefMAT – Cefas Marine Assessment Toolhttp://emeco.azurewebsites.net/

EMODNET - European Marine Observation and Data Network

* Would not be funded under current predicted sponsorship income