P3: DAC Work Programme timeline 2019-20

Activities in purple text are new to the DAC work plan, with the publication of the new MEDIN Business Plan 2019-2024.

Activities in grey cells with italics are at risk if the MEDIN budget does not receive increased funding.

| Activity | Apr-19 | May-19 | Jun-19 | Jul-19 | Aug-19 | Sep-19 | Oct-19 | Nov-19 | Dec-19 | Jan-20 | Feb-20 | Mar-20 | Ongoing? | Status Dec 2019 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Maintain and expand a comprehensive DAC network |  |  |  |  |  |  |  |  |  |  |  |  | Y |  |
| Increase the proportion of directly available datasets (2 clicks to data). |  |  |  |  |  |  |  |  |  |  |  |  | Y |  |
| Validation of portal metadata records |  |  |  |  |  |  |  |  |  |  |  |  | Y |  |
| DAC annual report collation and writing |  |  |  |  |  |  |  |  |  |  |  |  | Y | Done |
| Review progress with NI FishDAC accreditation |  |  |  |  |  |  |  |  |  |  |  |  | Y |  |
| DAC WG meeting |  |  |  |  |  |  |  |  |  |  |  |  | Y | Done |
| Launch small data archiving projects* |  |  |  |  |  |  |  |  |  |  |  |  |  | Delayed |
| Deliver progress report on MCZ/MPA data archiving |  |  |  |  |  |  |  |  |  |  |  |  | Y | Done |
| MSFD datasets to be managed in DAC network |  |  |  |  |  |  |  |  |  |  |  |  | Y |  |
| NEW: Review implications of cloud adoption in the DAC network i.e. revise MEDIN accreditation should a DAC use cloud technology.* |  |  |  |  |  |  |  |  |  |  |  |  | N | Not started |
| NEW: Develop a DAC-wide approach to provenance tracking. |  |  |  |  |  |  |  |  |  |  |  |  | N | Started |
| NEW: Proactively identify, target and engage with new suppliers to get their data on the MEDIN portal |  |  |  |  |  |  |  |  |  |  |  |  | Y |  |
| NEW: Develop a data ingestion model, covering costs, timescales and capabilities for all DACs.* |  |  |  |  |  |  |  |  |  |  |  |  | Y | Not started |
| NEW: Horizon scanning for new technology approaches e.g. schema.org, so that MEDIN is prepared to adapt to advances in technology. |  |  |  |  |  |  |  |  |  |  |  |  | Y | Started |
| DAC work plan 2020-21 |  |  |  |  |  |  |  |  |  |  |  |  | Y |  |

* Would not be funded under current predicted sponsorship income