DACs Activities and Timeline 2020-24

|  | Activity | Task | Apr-20 | Jul-20 | Oct-20 | Jan-21 | Apr-21 | Jul-21 | Oct-21 | Jan-22 | Apr-22 | Jul-22 | Oct-22 | Jan-23 | Apr-23 | Jul-23 | Oct-23 | Jan-24 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | 7.2 | Maintain a comprehensive DAC network (Operational) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Development | 6.2 | Horizon scanning for new technology approaches e.g. schema.org, so that MEDIN is prepared to adapt to advances in technology. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 11.1 | All DACs to provide Open Geospatial Consortium (OGC) compliant view and download services. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.6 | Strengthen and formalise the triage process for archiving multidisciplinary datasets (develop workflow). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.7 | Include persistent identifiers for dataset submissions, enabling linked data usage. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 11.4 | Increase the proportion of directly available datasets (2 clicks to data). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 11.7 | Develop a DAC-wide approach to provenance tracking. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 6.5 | Define an API structure for all DACS to adopt. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 11.5 | Ensure frictionless recovery of data by streamlining processes and promoting adoption of APIs across DACs and help them implement it. | Pushed back to Year 3 to allow for 6.5 to happen |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 1.10 | Identify master datasets and deliver them through the MEDIN infrastructure, making all necessary changes as required.* | Pushed back to start mid-Year 3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | 2.10 | Provide a data ingestion model, covering costs, timescales and capabilities for all DACs.* | Pushed back to start Year 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

* Lower priority activity that could only start in 2020/21 if additional funding was available, therefore pushed to start later in Work Plan.