1.1 WS2 Standards for data and metadata
The main objectives for the standards work-stream in 2010-11 are to continue to develop and maintain standards and guidelines for data and metadata to ensure data can be easily located and re-used. These standards will be developed to be consistent with guidelines and implementation rules as they emerge from INSPIRE and other relevant national and international standards initiatives. MEDIN standards work will also support developments within the UK Location Programme. Specific activities for 2010-11 are:  
· To develop, approve and publish data guidelines for Noise, Phytoplankton and Leisure and Recreation.

· To carry out practical reviews of existing data guidelines.

· To hold a workshop if deemed necessary to consider requirements for multi-beam echo sounder data, and (in cooperation with WS1) engage all relevant UK partners to develop a common strategy for processing and archiving these data.

· To develop further tools to support the generation of MEDIN format metadata from GIS and other applications.

· To encourage widespread adoption of MEDIN standards through the dissemination of publicity material.

£100,009 is provisionally allocated this Work Stream:




Core Team Staff costs (105 days): 
 
  £54,634




Travel and workshop costs: 
   

    £2,000




Funds for contracted work:


  £40,000




Total





  £96,634

The £40,000 for contracted work will be allocated to develop and review new standards.
Initial STDs WG Deliverables table
	Deliverable
	Status
	Commentary

	Q1

Hold MEDIN Standards Meeting

Complete upgrades to ArcCatalog and on-line metadata generation tools

Give MEDIN standards presentation at ISO meeting

Agree contract specification for new data guidelines and review of data guidelines

Revise Data Guidelines into new agreed structure
	
	KPI 1

	Q2

Produce and distribute MEDIN standards leaflets

Maintain Discovery Standard

Let contracts to review existing and derive new Data Guidelines

Three to Five year forward look for STDs work
	
	KPI 1

KPI4, KPI5

	Q3

Revise Data Guidelines in light of reviews

Hold workshop if necessary on multibeam echosounder data.

Hold MEDIN standards meeting
	
	

	Q4

Production of Geophysical Survey Data Guidelines

STDs Work Plan for 2011-2012

STDs Report for 2010-11
	
	


